## Sheet1
Week | Project | Owner | Tasks Completed | Issues | Next Steps | Status
2025-10-13 | Marketing Campaign | Dana | Finalized ad copy; scheduled posts | Delay in vendor approval | Launch campaign next week | On Track
2025-10-13 | Data Pipeline | Alex | Cleaned raw data; built staging table | None | Begin modeling phase | On Track
2025-10-13 | Sales Dashboard | Jordan | Updated visuals; added filters | Low engagement from team | Schedule demo with sales leads | Needs Attention
2025-10-13 | HR Metrics | Sam | Pulled retention data; formatted tables | Missing some data from Q2 | Follow up with HR for Q2 report | Delayed
2025-10-13 | Budget Review | Taylor | Updated spend tracker | None | Present summary to execs | Complete